| COmmittee/ Group/ Region: |  | Executive Council | Date: |
| --- | --- | --- | --- |
| Title: |  |  |  |
| ENCLOSURES: |  |  |  |
| 1. Background: |  |  |  |
| 2. Purpose |  |  |  |
| 3. EXECUTION: - METHOD: B. PROJECT DEVELOPMENT: PHASE I (Preparation Phase, [timetable]): PHASE II (Execution Phase, [timetable]): . PHASE III (Review Phase [timetable]): C. TASKS: |  |  |  |
| Officers | - President: - President elect: - Secretary: - Treasurer: |  |  |
| Region Representatives | - |  |  |
| Constitution & By-Laws | - |  |  |
| GAC |  |  |  |
| Membership |  |  |  |
| Public Relations |  |  |  |
| CUATC |  |  |  |
| Scholarship |  |  |  |
| Honors & Awards |  |  |  |
| Student Affairs |  |  |  |
| CEP |  |  |  |
| Annual Meeting |  |  |  |
| COORDINATING INSTRUCTIONS: TIMELINE: 5 March 12: Submit request to Officers 7 March 12: EC will discuss if changes are needed and proceed 12 March 12: President will assign members to task group 4 April 12: Initial revisions submitted to EC 21 APRIL 12: Final recommendations submitted to EC 5 MAY 12: Project complete |  |  |  |
| 4. Funding and Budget: This will be a zero cost and zero income project |  |  |  |
| 5. PROJECT GROUP DETAILS: - Project leader: Jay Sedory, President Elect, 434-262-6151 cell - Project group: 2 EC members, 2 regular members, 1 committee chair |  |  |  |